## Slide 1: Metrics for Project Size Estimation
5.7.2 Heuristic Techniques
Single Variable Model
Estimated Parameter = C1*ed1
Where,
e: characteristics of software which has been already estimated
Estimated parameter is dependent parameter to be estimated (e.g. effort, duration, staff size)
C1 & D1 are constants values collected from past projects / historical data
E.g. COCOMO model
Multi Variable Model
Estimated Resources=C1*ep1d1 +C2*ep2d2 + …
Where,
Ep1,ep2-Basic characteristics of the software already estimated
C1,C2,D1,D2,… are constants
It gives more accurate estimation.
E.g. Intermediate COCOMO model.

## Slide 2: Metrics for Project Size Estimation
5.7.2 Heuristic Techniques
1) COnstructive COst estimation MOdel (COCOMO)
Any software development project can be classified into any one of the following three categories based on the development complexity:
Complexity can be of three types: Organic, Semidetached and Embedded
We are categorizing the software which is to be developed in three categories:
Application Programs: e.g. Word processing software, accounting software etc.
Utility Programms: e.g. Compiler, linker etc.
System Softwares: e.g. real time system, operating system etc.
The ratio of development complexity is: 1:3:9
That means if any application software which requires say ‘X’ efforts to develop then utlity software will require 3X times efforts and 9X times efforts for system softwares.

## Slide 3: Metrics for Project Size Estimation
5.7.2 Heuristic Techniques
COnstructive COst estimation MOdel (COCOMO) (Cont.)
A) Organic: < 50 K LOC (e.g. Pay Load System)
well-understood application
Development team size is reasonably small
Experienced team members
B) Semidetached: 50 K < LOC < 300 K (e.g. Compiler)
Mixture of experienced and inexperienced development team
Limited experience on related system development.
Unfamiliar with some aspects of system being developed.
C) Embedded: LOC > 300 K (ATM, Air traffic control system)
- If the software being developed its strongly coupled to complex hardware, or if stringent regulations on the operation exist

## Slide 4: Metrics for Project Size Estimation
5.7.2 Heuristic Techniques
COnstructive COst estimation MOdel (COCOMO) (Cont.)
Basic COCOMO Model:
Gives estimate about project parameter
Effort= a1 x (KLOC)a2 PM (Person months)
Tdev = b1 x (effort)b2 Months
Where, KLOC - estimated size of software in Kilo Lines of Code
a1,a2,b1,b2 – constants for each software product category
Tdev – estimated time to develop (in Months)
Efforts – efforts required to develop (in Person Months)
 | Development effort estimation | Development time estimation
Organic | 2.4 (KLOC)1.05 PM | 2.5 (effort)0.38 Months
Semidetached | 3.0 (KLOC)1.12 PM | 2.5 (effort)0.35 Months
Embedded | 3.6 (KLOC)1.20 PM | 2.5 (effort)0.32 Months

## Slide 5: Metrics for Project Size Estimation
5.7.2 Heuristic Techniques
COnstructive COst estimation MOdel (COCOMO) (Cont.)
Basic COCOMO Model:
Ex: Assume that the size of an organic type of software product has been estimated to be 32,000 lines of source code. Assume that the average salary of software developers in Rs. 15,000 per month. Determine the effort required to develop the software product, the nominal development time, and the cost of develop the product.
Solution:
Efforts = 2.4 x (32)1.05 = 91 Person Months (PM)
Nominal development time = 2.5 x (91)0.38 = 14 Months
Cost = 91 x 15,000 = Rs. 1,465,000

## Slide 6: Metrics for Project Size Estimation
5.7.2 Heuristic Techniques
COnstructive COst estimation MOdel (COCOMO) (Cont.)
Intermediate COCOMO Model:
Basic COCOMO assumes that effort and development time are functions of the product size alone.
The intermediate COCOMO model recognize all other project parameters which may affect effort and development time; It refines the initial estimate obtained using the basic COCOMO expression by using a set of 15 cost drivers (multipliers) based on various attributes of software development
Different cost drivers:
Product related: complexity of the product, reliability
Computer related: Execution speed, storage space etc.
Personnel related: experience level, programming / analysis capability
Development environment related: automation tools (e.g. CASE tool)

## Slide 7: Metrics for Project Size Estimation
5.7.3 Analytical Estimation Techniques : Halstead’s software science
To measure size, development effort, and development cost of software products
For a given program, Let
n1- no. of unique operators used in the program
n2- no. of unique operands used in the program
N1- total no. of operators used in the program
N2- total no. of operands used in the program
How to identify operators?
Arithmetic, Logical, assignment operators
() and {}
Label of GOTO statement
If, if…then…else…endif, while, for, do ;
How to identify operands?
Function name, variable name, function name in function call, arguments in function call
But remember…! Parameter list in function declaration is not considered as operands

## Slide 8: Metrics for Project Size Estimation
5.7.3 Analytical Estimation Techniques : Halstead’s software science
Length and vocabulary:
Length of a program (N) = N1 + N2
Program’s vocabulary (n) = n1+n2
Program’s Volume:
Length of a program depends on choice of operators and operands
For the same programming problem, length of program may differ because of programming style and programming language used
V = N Log2 n where V - min. no. of bits need to encode the program
n - unique different identifiers / program’s vocabulary
So, we need N Log2 n bits to store a program having length N
c) Potential Minimum Volume:
The potential minimum volume V* is defined as the volume of the most succinct program in which a problem can be coded. The minimum volume is obtained when the program can be expressed using a single source code instruction, say a function call like foo ();
Thus if an algorithm operates on input and output data (d1, d2, … , dn) the most succinct program would be f(d1,d2,…,dn); for which n1=2, n2=n therefore

## Slide 9: Metrics for Project Size Estimation
5.7.3 Analytical Estimation Techniques : Halstead’s software science
V* = ( 2 + n2 ) Log2 ( 2 + n2 )
Program level L=V*/V
Higher the program level → less effort to develop
d) Efforts and Time:
Efforts need to develop a program E = V (volume of the program) / L (Level of programming lang. used)
E=V2/V (where E is no. of mental discrimination required to implement the program and also the effort required to read and understand the program.)
T=E/S (S-speed of mental discriminations S=18 empirically psychologically decided)
e) Length Estimation:
Halstead suggests a way to determine the length of a program using the no. of unique operators and operands used in the program.
By this method, length, cost, volume, efforts etc. can be determined before even starting the programming.
Any program of length N consist of N/n unique strings of n (length). Now it is standard combinational result that for any given alphabet of size K, these are exactly Kr different strings of length r. Thus

## Slide 10: Metrics for Project Size Estimation
5.7.3 Analytical Estimation Techniques : Halstead’s software science
N/n ≤ nn or N ≤nn+1
Upper bound can be (as operators and operands may duplicates)
So N ≤ nn1n1n2n2
N must include all possible subsets of that ordered set.
2N=nn1n1n2n2
Take log both side: N=log2n+log2(n1n1n2n2)
So we get, N=log2(n1n1n2n2) (approxing ignoring log2N)
Or N = log2n1n1+log2n2n2 = n1log2n1 + n2log2n2
Ex. Find out estimated length and volume of following C program
main()
{
int a, b, c, avg;
scanf(“%d %d %d”, &a, &b, &c);
avg=(a+b+c)/3;
printf(“avg=%d”,avg);
}

## Slide 11: Metrics for Project Size Estimation
5.7.3 Analytical Estimation Techniques : Halstead’s software science
Solution:
Step-1: First, Find out the total number of unique operators used: 12
main, (), {}, int, scanf, &, “,”, “;”, = , +, /, printf
Step-2: Find out the total number of unique operands used:11
“%d %d %d”,a+b+c, a, b, c, &a, &b, &c, avg=%d, avg, 3
Step-3: Therefore, here n1=12, n2=11
Now, estimated length (N) = n1log2n1 + n2log2n2
=(12*log212) + (11*log211)
=43+38
=81
Volume(V) = N * Log2 n
= 81 * log2(23)
= 81 * 4.52
= 366

## Slide 12: Metrics for Project Size Estimation
5.8 Scheduling
Scheduling defines that which task should be taken up when
How to schedule project activities:
Identify all tasks needed to complete the project.
Breakdown large task into small activities.
Determine the dependency among different activities
Establish the most likely estimates for the time duration necessary to complete the activities
Allocate resources to activities
Plan the starting and ending dates for various activities
Determine the critical path: A critical path is a chain of activities that determines the duration of project.
The end of each activity is called Milestone

## Slide 13: Metrics for Project Size Estimation
5.8 Scheduling
5.8.1 Work Breakdown Structure
- Work breakdown structure (WBS)
is used to recursively decompose
a given set of activities into
smaller activities.
First, let us understand why it
Is necessary to break down project
Activities into tasks.
[Figure 5.1 MIS Problem]
- Once project Activities have been decomposed into a set of Tasks using WBS, the time frame when each activity is to be performed is to be determined. The end of each important activity is called a milestone. The project manager tracks the progress of a project by monitoring the timely completion of the milestones. If he observes that some milestones start getting delayed, he carefully monitors and controls the progress of the tasks, so that the overall deadline can still be met
MIS Application
Requirement Specification
Design
Code
Test
Document
Database Part
Graphical User Interface Part
Database Part
Graphical User Interface Part

## Slide 14: Metrics for Project Size Estimation
5.8 Scheduling
5.8.2 Activity Networks:
Minimum time: the maximum of all paths from start to finish
So, Here its ( 15 + 45 + 105 + 120 ) = 285
[Figure 5.2 Activity Network]
Specification
15
Design Database
45
Code Database
105
Design GUI
30
Code GUI
45
Integrate and test
120
Finish
0
Write User Manual
60
Task No. | Task | Duration | Dependency
T1 | Specification | 15 | -
T2 | Design Database | 45 | T1
T3 | Design GUI | 30 | T1
T4 | Code Database | 105 | T2
T5 | Code GUI Part | 45 | T3
T6 | Integrate and Test | 120 | T4 & T5
T7 | Write User Manual | 60 | T1

## Slide 15: Metrics for Project Size Estimation
5.8 Scheduling
5.8.2 Critical Path Method (CPM):
A path in the activity network graph is any set of consecutive nodes and edges in this graph from the starting node to the last node.
A critical path consists of a set of dependent tasks that need to be performed in a sequence and which together take the longest time to complete.
A Critical task is one with a zero slack time. A path from the start node to the finish node containing only critical tasks is called a critical path.
Minimum time (MT): It is the minimum time required to complete the project. It is computed by determining the maximum of all paths from start to finish.
Earliest start (ES): It is the time of a task is the maximum of all paths from the start to this task. The ES for a task is the ES of the previous task plus the duration of the preceding task.
Latest start time (LST): It is the difference between MT and the maximum of all paths from this task to the finish. The LST can be computed by subtracting the duration of the subsequent task from the LST of the subsequent task.
Earliest finish time (EF): The EF for a task is the sum of the earliest start time of the task and the duration of the task.
Latest finish (LF): LF indicates the latest time by which a task can finish without affecting the final completion time of the project. A task completing beyond its LF would cause project delay. LF of a task can be obtained by subtracting maximum of all paths from this task to finish from MT.
Slack time (ST): The slack time (or float time) is the total time that a task may be delayed before it will affect the end time of the project. The slack time indicates the ”flexibility” in starting and completion of tasks. ST for a task is LS-ES and can equivalently be written as LF-EF.

## Slide 16: Metrics for Project Size Estimation
5.8 Scheduling
5.8.2 Critical Path Method (CPM):
Example : Use the Activity network of Figure 5.2 to determine the ES and EF for every task for the MIS problem
Solution:
[ Figure 5.3 Finding Early Start (ES) and Early Finish (ES) ]
(ES, EF) Specification
0 , 15
Design Database
15 , 60
Code Database
60 , 165
Design GUI
15 , 45
Code GUI
45 , 90
Integrate and test
165 , 285
Finish
285 , 285
Write User Manual
15 , 75

## Slide 17: Metrics for Project Size Estimation
5.8 Scheduling
5.8.2 Critical Path Method (CPM):
Example: Use the same Activity network of Figure 5.3 to determine the LS, LF and ST for every task for the MIS problem (Remember that our Minimum Time (MT) was 285)
What is Latest Start (LS)? Difference between MT and max of all paths from this task to finish
What is Latest Finish (LF)? MT – (max of all paths from this task to finish)
Task | ES | EF | LS | LF | ST
Specification | 0 | 15 |  |  | 
Design Database | 15 | 60 |  |  | 
Design GUI | 15 | 45 |  |  | 
Code Database | 60 | 165 |  |  | 
Code GUI Part | 45 | 90 |  |  | 
Integrate and Test | 165 | 285 |  |  | 
Write User Manual | 15 | 75 |  |  | 

## Slide 18: Metrics for Project Size Estimation
5.8 Scheduling
5.8.2 Critical Path Method (CPM):
Solution:
[ Figure 5.3 Finding Early Start (ES) and Early Finish (ES) ]
(LS, LF) Specification
0, 15
Design Database
15 , 60
Code Database
60 , 165
Design GUI
90 , 120
Code GUI
120 , 165
Integrate and test
165 , 285
Finish
285, 285
Write User Manual
225, 285
Task | ES | EF | LS | LF | ST (LF-EF)
Specification | 0 | 15 | Difference (285,285) = 0 | 285-(45+105+120)=15 | 15-15=0
Design Database | 15 | 60 | Difference (285,(45+105+120 )) = 15 | 285-(105+120)=60 | 60-60=0
Design GUI | 15 | 45 | Difference (285, (30+45+120)) = 90 | 285-(45+120)=120 | 120-45=75
Code Database | 60 | 165 | Difference (285,(105+120)) =60 | 285-(120)=165 | 165-165=0
Code GUI Part | 45 | 90 | Difference (285, (45+120))=120 | 285-(120)=165 | 165-90=75
Integrate and Test | 165 | 285 | Difference (285, 120) = 165 | 285-(0)=285 | 285-285=0
Write User Manual | 15 | 75 | Difference (285, 60) = 225 | 285-(0)=285 | 285-75=210

## Slide 19
Gantt Chart
Used to allocate resources to activities
Shaded part shows length of time where as white bar shows slack time
PERT chart
Project Evaluation and Review Technique chart
It represents statistical variation in the project estimates assuming a normal distribution
5.8.2 Gantt Chart and PERT Chart
Metrics for Project Size Estimation
5.8 Scheduling